## Specifications
Project Name：Robot Arm

## Block Diagram
Bluetoothmodule
| FUNCTION | Descciption
| Buck Power Module | 1

## Schedule
任務名稱 | 工作天數 | 開始時間 | 結束時間 | 備註
電腦介面控制機器手臂 | 8 工作日? | 110/3/8 | 110/3/17
確定規格及功能 | 4 工作日 | 110/3/8 | 110/3/11
畫出功能方塊圖 | 3 工作日 | 110/3/8 | 110/3/10
解析功能方塊圖 | 3 工作日 | 110/3/11 | 110/3/15
規劃時程 | 3 工作日 | 110/3/11 | 110/3/15
硬體 | 8 工作日? | 110/3/8 | 110/3/17
硬體規格描述 | 1 工作日? | 110/3/8 | 110/3/8
零件規格書 | 4 工作日? | 110/3/8 | 110/3/11
零件的Symbol | 4 工作日 | 110/3/8 | 110/3/11
零件的Footprint | 1 工作日? | 110/3/8 | 110/3/8
硬體線路圖 | 1 工作日? | 110/3/12 | 110/3/12
PCB layout | 1 工作日? | 110/3/15 | 110/3/15
洗PCB | 1 工作日? | 110/3/16 | 110/3/16
準備零件 | 1 工作日? | 110/3/9 | 110/3/9
焊接 | 1 工作日? | 110/3/17 | 110/3/17
軟體 | 3 工作日? | 110/3/8 | 110/3/10
軟體功能描述 | 1 工作日? | 110/3/8 | 110/3/8
GUI的規格 | 1 工作日? | 110/3/8 | 110/3/8
PWM | 2 工作日 | 110/3/8 | 110/3/9
UART | 1 工作日? | 110/3/10 | 110/3/10
研究規格書 | 1 工作日? | 110/3/10 | 110/3/10
UART Tx | 1 工作日? | 110/3/10 | 110/3/10
UART Rx | 1 工作日? | 110/3/10 | 110/3/10
機構 | 1 工作日? | 110/3/8 | 110/3/8
基座 | 1 工作日? | 110/3/8 | 110/3/8
手臂 | 1 工作日? | 110/3/8 | 110/3/8
手指 | 1 工作日? | 110/3/8 | 110/3/8

## Status Review
State | Date | Status Descriptions | Actions Items | Comments
Open | 2021-04-02 |  | 1. 確定需要使Deepp Learning or OpenCv? If 使用Deep Learning 1.確定使用哪種Algorithm? a. 影像辨識 b. 影像偵測 c. 3D影像辨識 d. 手勢辨識 2. 使用何種框架? A. Tensorflow or Yolo?

## Issues Tracking
Item | Status | Priority | Descriptions of Issue | Open Date | Due Date | Close Date | Owner | Comments

## Pin Definition
Pin No. | 1st Function | 2nd Function | 3rd Function | 4th Function | 5th Function | Robot Arm | HW signal Name
1
2
3
4
5
6
7

## Notice
Date | Descriptions | Comments
2021-03-04

## DC-DC Conveter
referenceweb

## Check List Format
Section | Items | Checking Item Descriptions | Check | Detailed Comments | Attached Report

## Feasibility
Rpi or PC ?