## Schedule
任務名稱 | 工作天數 | 開始時間 | 結束時間 | 備註
機器手 | 141 工作日 | 110/5/10 | 110/11/20
確定規格及功能 | 4 工作日 | 110/5/10 | 110/5/13
畫出功能方塊圖 | 2 工作日 | 110/5/14 | 110/5/17
解析功能方塊圖 | 2 工作日 | 110/5/18 | 110/5/19
規劃時程 | 3 工作日 | 110/5/18 | 110/5/20
硬體 | 26 工作日 | 110/5/20 | 110/6/24
硬體規格描述 | 3 工作日 | 110/5/20 | 110/5/24
零件規格書 | 7 工作日 | 110/5/20 | 110/5/28
硬體線路圖 | 7 工作日 | 110/5/26 | 110/6/3
PCB layout | 6 工作日 | 110/6/4 | 110/6/11
洗PCB | 5 工作日 | 110/6/14 | 110/6/18
準備零件 | 5 工作日 | 110/5/25 | 110/5/31
焊接 | 4 工作日 | 110/6/21 | 110/6/24
軟體 | 5 工作日 | 110/5/20 | 110/5/26
軟體功能描述 | 2 工作日 | 110/5/20 | 110/5/21
GUI的規格 | 3 工作日 | 110/5/24 | 110/5/26
PWM | 2 工作日 | 110/5/24 | 110/5/25
UART | 3 工作日 | 110/5/24 | 110/5/26
研究規格書 | 1 工作日 | 110/5/24 | 110/5/24
MCU傳送資料到Arduino | 1 工作日 | 110/5/25 | 110/5/25
MCU接收Arduino資料 | 1 工作日 | 110/5/26 | 110/5/26
機構 | 46 工作日 | 110/5/20 | 110/7/22
基座 | 30 工作日 | 110/5/20 | 110/6/30
手腕 | 6 工作日 | 110/7/1 | 110/7/8
手臂 | 5 工作日 | 110/7/9 | 110/7/15
手指 | 5 工作日 | 110/7/16 | 110/7/22
材料、零件準備 | 32 工作日 | 110/5/25 | 110/7/7
HT66F2390 CPU | 7 工作日 | 110/5/25 | 110/6/2
FR4 PCB | 6 工作日 | 110/5/25 | 110/6/1
壓克力 | 5 工作日 | 110/7/1 | 110/7/7
與主辦單位有關事項 | 133 工作日 | 110/5/20 | 110/11/20
初賽報告上傳 (by 5/31) | 8 工作日 | 110/5/20 | 110/5/31
主辦單位初賽審核 | 9 工作日 | 110/6/2 | 110/6/14
主辦單位公布複賽名單 | 1 工作日 | 110/6/16 | 110/6/16
複賽報告上傳(by 10/27) | 2 工作日 | 110/10/21 | 110/10/22
作品照片與決賽海報上傳 (by 10/31) | 5 工作日 | 110/10/25 | 110/10/29
作品影片上傳 (by 11/12) | 8 工作日 | 110/11/1 | 110/11/10
複賽正式比賽 | 1 工作日 | 110/11/20 | 110/11/20

## Status Review
State | Date | Status Descriptions | Actions Items | Comments
Open | 2021-03-07 | 描述功能規格
Open | 2021-03-07 | 畫功能方塊圖
Open | 2021-03-07 | 解析功能方塊圖
Open | 2021-05-10 | 初賽報告

## Issues Tracking
Item | Status | Priority | Descriptions of Issue | Open Date | Due Date | Close Date | Owner | Comments

## Notice
Date | Descriptions | Comments

## Specifications
Project Name：Robot Arm

## Pin Definition
Pin No. | 1st Function | 2nd Function | 3rd Function | 4th Function | 5th Function | Robot Arm
1
2
3
4
5
6
7

## Check List Format
Section | Items | Checking Item Descriptions | Check | Detailed Comments | Attached Report